## DP00
ACT | TITLE | CNTR | WORK | OD
---------- | ------------------------------------------------ | ----- | ----- | -----
0 | START OF NETWORK |  |  | 1
80 | END OF NETWORK |  |  | 1
0 1 | CLEAR SITE | 1 | 1 | 3
0 210 | SUBMIT FOUNDATION REBAR |  |  | 10
0 212 | SUBMIT STRUCTURAL STEEL |  |  | 20
0 214 | SUBMIT CRANE |  |  | 20
0 216 | SUBMIT BAR JOISTS |  |  | 20
0 218 | SUBMIT SIDING |  |  | 20
0 220 | SUBMIT PLANT ELECTRICAL LOAD CENTER |  |  | 20
0 222 | SUBMIT POWER PANELS - PLANT |  |  | 20
0 224 | SUBMIT EXTERIOR DOORS |  |  | 20
0 225 | SUBMIT PLANT ELECTRICAL FIXTURES |  |  | 30
0 227 | SUBMIT PLANT HEATING AND VENTILATING FANS |  |  | 20
0 229 | SUBMIT BOILER |  |  | 20
0 231 | SUBMIT OIL TANK |  |  | 20
0 233 | SUBMIT PRECAST |  |  | 40
0 235 | SUBMIT PACKAGED A/C |  |  | 30
1 2 | SURVEY AND LAYOUT | 1 | 2 | 2
2 3 | ROUGH GRADE | 1 | 1 | 2
3 4 | DRILL WELL | 1 | 9 | 15
3 6 | WATER TANK FOUNDATIONS | 1 | 3 | 4
3 9 | EXCAVATE FOR SEWER | 1 | 1 | 10
3 10 | EXCAVATE ELECTRIC MANHOLES | 1 | 1 | 1
3 12 | OVERHEAD POLE LINE | 1 | 4 | 6
4 5 | INSTALL WELL PUMP | 1 | 9 | 2
5 8 | UNDERGROUND WATER PIPING | 1 | 5 | 8
6 7 | ERECT WATER TANK | 1 | 10 | 10
7 8 | TANK PIPING & VALVES | 1 | 10 | 10
8 13 | CONNECT WATER PIPING | 1 | 10 | 2
9 11 | INSTALL SEWER AND BACKFILL | 1 | 5 | 5
10 11 | INSTALL ELECTRICAL MANHOLES | 1 | 4 | 5
11 12 | INSTALL ELECTRICAL DUCT BANK | 1 | 4 | 3
12 13 | PULL IN FEEDER | 1 | 4 | 5
13 14 | BUILDING LAYOUT | 2 | 2 | 1
14 15 | DRIVE AND POUR PILES | 2 | 11 | 10
14 23 | EXCAVATE FOR OFFICE BUILDING | 2 | 1 | 3
15 16 | EXCAVATE PLANT WAREHOUSE | 2 | 1 | 5
16 17 | POUR PILE CAPS P-W | 2 | 3 | 5
17 18 | FORM AND POUR GRADE BEAMS P-W | 2 | 3 | 10
18 19 | BACKFILL AND COMPACT P-W | 2 | 1 | 3
18 21 | FORM AND POUR RAILROAD LOADING DOCK P-W | 2 | 3 | 5
18 22 | FORM AND POUR TRUCK LOADING DOCK P-W | 2 | 3 | 5
19 20 | UNDERSLAB PLUMBING P-W | 2 | 5 | 5
20 22 | UNDERSLAB CONDUIT P-W | 2 | 4 | 5
21 22 |  |  |  | 0
22 29 | FORM AND POUR SLABS P-W | 2 | 3 | 10
23 24 | SPREAD FOOTINGS OFFICE | 2 | 3 | 4
24 25 | FORM AND POUR GRADE BEAMS OFFICE | 2 | 3 | 6
25 26 | BACKFILL AND COMPACT OFFICE | 2 | 1 | 1
26 27 | UNDERSLAB PLUMBING OFFICE | 2 | 5 | 3
27 28 | UNDERSLAB CONDUIT OFFICE | 2 | 4 | 3
28 99 | FORM AND POUR SLABS OFFICE | 2 | 3 | 3
29 30 | ERECT STRUCTURAL STEEL P-W | 3 | 6 | 10
30 31 | PLUMB AND BOLT STEEL P-W | 3 | 6 | 5
31 32 | ERECT CRANEWAY AND CRANE P-W | 3 | 6 | 5
31 33 | ERECT MONORAIL TRACK P-W | 3 | 6 | 3
32 33 |  |  |  | 0
33 34 | ERECT BAR JOISTS P-W | 3 | 6 | 3
34 35 | ERECT ROOF PLANKS P-W | 3 | 7 | 3
35 36 | ERECT SIDING P-W | 3 | 12 | 10
35 37 | BUILT-UP ROOFING P-W | 3 | 13 | 5
36 37 |  |  |  | 0
37 80 | PERIMETER FENCE | 5 | 15 | 10
37 90 | PAVE PARKING AREA | 5 | 16 | 5
37 91 | GRADE AND BALLAST RAILROAD SIDING | 5 | 17 | 5
37 92 | ACCESS ROAD | 5 | 16 | 10
37 93 | AREA LIGHTING | 5 | 4 | 20
37 300 |  |  |  | 0
37 301 |  |  |  | 0
37 302 |  |  |  | 0
37 303 |  |  |  | 0
37 304 |  |  |  | 0
37 305 |  |  |  | 0
37 306 |  |  |  | 0
37 307 |  |  |  | 0
37 308 |  |  |  | 0
38 43 | INSTALL POWER CONDUIT P-W | 3 | 4 | 20
39 42 | FRAME CEILING P-W | 3 | 18 | 5
40 47 | TEST PIPING SYSTEMS P-W | 3 | 8 | 10
41 47 | PREOPERATIONAL CHECK | 3 | 8 | 5
42 44 | DRYWALL PARTITIONS P-W | 3 | 19 | 10
43 49 | INSTALL BRANCH CONDUIT P-W | 3 | 4 | 15
44 45 |  |  |  | 0
44 46 |  |  |  | 0
44 48 | CERAMIC TILE | 3 | 20 | 10
44 58 | HANG INTERIOR DOORS P-W | 3 | 21 | 10
45 51 | ROOM OUTLETS P-W | 3 | 4 | 5
46 52 | INSTALL DUCTWORK P-W | 3 | 8 | 25
47 58 | LIGHT OFF BOILER AND TEST | 3 | 8 | 5
48 53 | PAINT ROOMS P-W | 3 | 22 | 5
49 45 |  |  |  | 0
49 50 | PULL WIRE P-W | 3 | 4 | 15
50 54 | INSTALL PANEL INTERNALS P-W | 3 | 4 | 5
51 56 | INSTALL ELECTRICAL FIXTURES | 3 | 4 | 10
52 58 | INSULATE HEATING AND VENTILATING SYSTEM P-W | 3 | 8 | 15
53 57 | FLOOR TILE P-W | 3 | 22 | 10
53 58 | INSTALL PLUMBING FIXTURES P-W | 3 | 5 | 10
54 55 | TERMINATE WIRE P-W | 3 | 4 | 10
55 56 | RING OUT P-W | 3 | 4 | 10
56 58 | ENERGIZE POWER | 3 | 4 | 1
57 58 | INSTALL FURNISHINGS P-W | 3 | 24 | 10
58 80 | ERECT FLAGPOLE | 5 | 29 | 5
58 94 | FINE GRADE | 5 | 1 | 5
59 60 | ERECT PRECAST ROOF OFFICE | 4 | 7 | 5
60 61 | EXTERIOR MASONRY OFFICE | 4 | 14 | 10
60 76 | INSTALL PACKAGE AIR CONDITIONING | 4 | 8 | 5
61 62 | EXTERIOR DOORS OFFICE | 4 | 21 | 5
61 63 | PLACE SINGLE-PLY ROOFING OFFICE | 4 | 17 | 5
61 64 | INSTALL PIPING OFFICE | 4 | 8 | 10
61 65 | INSTALL BACKING BOXES | 4 | 4 | 4
61 68 | GLAZE OFFICE | 4 | 25 | 5
61 77 | DUCTWORK OFFICE | 4 | 8 | 15
62 63 |  |  |  | 0
63 68 |  |  |  | 0
63 80 | PAINT EXTERIOR OFFICE | 4 | 22 | 5
64 67 | TEST PIPING OFFICE | 4 | 8 | 4
65 66 | INSTALL CONDUIT OFFICE | 4 | 4 | 10
66 67 |  |  |  | 0
66 74 | PULL WIRE OFFICE | 4 | 4 | 10
67 68 | METAL STUDS OFFICE | 4 | 19 | 5
68 69 | DRYWALL | 4 | 19 | 5
69 70 | DRYWALL | 4 | 19 | 10
69 73 | CERAMIC TILE OFFICE | 4 | 20 | 10
70 71 | WOOD TRIM OFFICE | 4 | 26 | 10
70 77 |  |  |  | 0
71 72 | PAINT INTERIOR OFFICE | 4 | 22 | 10
71 80 | HANG DOORS OFFICE | 4 | 21 | 5
72 73 |  |  |  | 0
72 78 |  |  |  | 0
72 80 | FLOOR TILE OFFICE | 4 | 20 | 10
73 80 | TOILET FIXTURES OFFICE | 4 | 5 | 5
74 75 | INSTALL PANEL INTERNALS OFFICE | 5 | 4 | 5
74 76 |  |  |  | 0
75 79 | TERMINATE WIRES OFFICE | 4 | 4 | 10
76 79 | A/C ELECTRICAL CONNECTIONS | 4 | 4 | 4
77 78 | INSTALL CEILING GRID OFFICE | 4 | 18 | 5
78 80 | ACOUSTIC TILES OFFICE | 4 | 18 | 10
79 80 | RING OUT | 4 | 4 | 5
90 58 |  |  |  | 0
91 58 | INSTALL RAILROAD SIDING | 5 | 17 | 10
92 58 |  |  |  | 0
93 80 |  |  |  | 0
94 80 | SEED AND PLANT | 5 | 27 | 5
99 59 | ERECT PRECAST STRUCTURE | 4 | 7 | 5
210 211 | APPROVE FOUNDATION REBAR |  |  | 10
211 16 | FAB/DEL FOUNDATION REBAR |  |  | 10
212 213 | APPROVE STRUCTURAL STEEL |  |  | 10
213 23 | FAB/DEL STRUCTURAL STEEL |  |  | 40
214 215 | APPROVE CRANE |  |  | 10
215 31 | FAB/DEL CRANE |  |  | 50
216 217 | APPROVE BAR JOISTS |  |  | 10
217 33 | FAB/DEL BAR JOISTS |  |  | 30
218 219 | APPROVE SIDING |  |  | 10
219 35 | FAB/DEL SIDING |  |  | 40
220 221 | APPROVE PLANT ELECTRICAL LOAD CENTER |  |  | 10
221 300 | FAB/DEL PLANT ELECTRICAL LOAD CENTER |  |  | 90
222 223 | APPROVE POWER PANELS - PLANT |  |  | 10
223 301 | FAB/DEL POWER PANELS - PLANT |  |  | 75
224 225 | APPROVE EXTERIOR DOORS |  |  | 10
225 226 | APPROVE PLANT ELECTRICAL FIXTURES |  |  | 15
225 302 | FAB/DEL EXTERIOR DOORS |  |  | 80
226 51 | FAB/DEL PLANT ELECTRICAL FIXTURES |  |  | 75
227 228 | APPROVE PLANT HEATING AND VENTILATING FANS |  |  | 10
228 304 | FAB/DEL PLANT HEATING AND VENTILATING FANS |  |  | 75
229 230 | APPROVE BOILER |  |  | 10
230 306 | FAB/DEL BOILER |  |  | 60
231 232 | APPROVE OIL TANK |  |  | 10
232 305 | FAB/DEL OIL TANK |  |  | 50
233 234 | APPROVE PRECAST |  |  | 10
234 99 | FAB/DEL PRECAST |  |  | 30
235 236 | APPROVE PACKAGED A/C |  |  | 10
236 60 | FAB/DEL PACKAGED A/C |  |  | 90
300 38 | SET ELECTRICAL LOAD CENTER | 3 | 4 | 2
301 43 | INSTALL POWER PANEL BACKING BOXES | 3 | 4 | 10
302 42 | EXTERIOR DOORS P-W | 3 | 6 | 5
303 39 | MASONRY PARTITIONS | 3 | 14 | 10
304 46 | INSTALL HEATING AND VENTILATING UNITS | 3 | 8 | 15
305 47 | INSTALL FUEL OIL TANK | 3 | 8 | 3
306 41 | ERECT BOILERS AND AUXILIARIES | 3 | 8 | 25
307 40 | FABRICATE PIPING SYSTEMS | 3 | 8 | 30
308 58 | INSTALL MONORAIL | 3 | 6 | 5