## DP00RES
ACT | TITLE | CNTR | WORK | RES | RID | RUT | UPT | BC
---------- | ------------------------------------------------ | ----- | ----- | -------- | --- | ---- | ------------- | -------------
0 | START OF NETWORK | [5 empty] | 0 | 0
80 | END OF NETWORK | [5 empty] | 0 | 0
0 1 | CLEAR SITE | 1 | 1 | COST |  |  | 0 | 28000
0 1 | CLEAR SITE | 1 | 1 | OP |  |  | 5 | 0
0 210 | SUBMIT FOUNDATION REBAR | [5 empty] | 0 | 0
0 212 | SUBMIT STRUCTURAL STEEL | [5 empty] | 0 | 0
0 214 | SUBMIT CRANE | [5 empty] | 0 | 0
0 216 | SUBMIT BAR JOISTS | [5 empty] | 0 | 0
0 218 | SUBMIT SIDING | [5 empty] | 0 | 0
0 220 | SUBMIT PLANT ELECTRICAL LOAD CENTER | [5 empty] | 0 | 0
0 222 | SUBMIT POWER PANELS - PLANT | [5 empty] | 0 | 0
0 224 | SUBMIT EXTERIOR DOORS | [5 empty] | 0 | 0
0 225 | SUBMIT PLANT ELECTRICAL FIXTURES | [5 empty] | 0 | 0
0 227 | SUBMIT PLANT HEATING AND VENTILATING FANS | [5 empty] | 0 | 0
0 229 | SUBMIT BOILER | [5 empty] | 0 | 0
0 231 | SUBMIT OIL TANK | [5 empty] | 0 | 0
0 233 | SUBMIT PRECAST | [5 empty] | 0 | 0
0 235 | SUBMIT PACKAGED A/C | [5 empty] | 0 | 0
1 2 | SURVEY AND LAYOUT | 1 | 2 | COST |  |  | 0 | 2500
1 2 | SURVEY AND LAYOUT | 1 | 2 | SV |  |  | 3 | 0
2 3 | ROUGH GRADE | 1 | 1 | COST |  |  | 0 | 10000
2 3 | ROUGH GRADE | 1 | 1 | OP |  |  | 3 | 0
3 4 | DRILL WELL | 1 | 9 | COST |  |  | 0 | 10000
3 4 | DRILL WELL | 1 | 9 | PB |  |  | 2 | 0
3 6 | WATER TANK FOUNDATIONS | 1 | 3 | COST |  |  | 0 | 5000
3 6 | WATER TANK FOUNDATIONS | 1 | 3 | CP |  |  | 4 | 0
3 6 | WATER TANK FOUNDATIONS | 1 | 3 | LB |  |  | 2 | 0
3 9 | EXCAVATE FOR SEWER | 1 | 1 | COST |  |  | 0 | 21500
3 9 | EXCAVATE FOR SEWER | 1 | 1 | OP |  |  | 5 | 0
3 10 | EXCAVATE ELECTRIC MANHOLES | 1 | 1 | COST |  |  | 0 | 1000
3 10 | EXCAVATE ELECTRIC MANHOLES | 1 | 1 | OP |  |  | 2 | 0
3 12 | OVERHEAD POLE LINE | 1 | 4 | COST |  |  | 0 | 30000
3 12 | OVERHEAD POLE LINE | 1 | 4 | EL |  |  | 4 | 0
4 5 | INSTALL WELL PUMP | 1 | 9 | COST |  |  | 0 | 11250
4 5 | INSTALL WELL PUMP | 1 | 9 | PB |  |  | 2 | 0
5 8 | UNDERGROUND WATER PIPING | 1 | 5 | COST |  |  | 0 | 18000
5 8 | UNDERGROUND WATER PIPING | 1 | 5 | PB |  |  | 2 | 0
6 7 | ERECT WATER TANK | 1 | 10 | COST |  |  | 0 | 225000
6 7 | ERECT WATER TANK | 1 | 10 | BM |  |  | 8 | 0
7 8 | TANK PIPING & VALVES | 1 | 10 | COST |  |  | 0 | 40000
7 8 | TANK PIPING & VALVES | 1 | 10 | BM |  |  | 4 | 0
8 13 | CONNECT WATER PIPING | 1 | 10 | COST |  |  | 0 | 2000
8 13 | CONNECT WATER PIPING | 1 | 10 | BM |  |  | 4 | 0
9 11 | INSTALL SEWER AND BACKFILL | 1 | 5 | COST |  |  | 0 | 65000
9 11 | INSTALL SEWER AND BACKFILL | 1 | 5 | PB |  |  | 6 | 0
10 11 | INSTALL ELECTRICAL MANHOLES | 1 | 4 | COST |  |  | 0 | 6500
10 11 | INSTALL ELECTRICAL MANHOLES | 1 | 4 | CP |  |  | 4 | 0
10 11 | INSTALL ELECTRICAL MANHOLES | 1 | 4 | LB |  |  | 2 | 0
11 12 | INSTALL ELECTRICAL DUCT BANK | 1 | 4 | COST |  |  | 0 | 7500
11 12 | INSTALL ELECTRICAL DUCT BANK | 1 | 4 | EL |  |  | 6 | 0
12 13 | PULL IN FEEDER | 1 | 4 | COST |  |  | 0 | 6000
12 13 | PULL IN FEEDER | 1 | 4 | EL |  |  | 4 | 0
13 14 | BUILDING LAYOUT | 2 | 2 | COST |  |  | 0 | 4000
13 14 | BUILDING LAYOUT | 2 | 2 | SV |  |  | 3 | 0
14 15 | DRIVE AND POUR PILES | 2 | 11 | COST |  |  | 0 | 70000
14 15 | DRIVE AND POUR PILES | 2 | 11 | OP |  |  | 2 | 0
14 15 | DRIVE AND POUR PILES | 2 | 11 | CP |  |  | 2 | 0
14 15 | DRIVE AND POUR PILES | 2 | 11 | LB |  |  | 2 | 0
14 23 | EXCAVATE FOR OFFICE BUILDING | 2 | 1 | COST |  |  | 0 | 27000
14 23 | EXCAVATE FOR OFFICE BUILDING | 2 | 1 | OP |  |  | 5 | 0
15 16 | EXCAVATE PLANT WAREHOUSE | 2 | 1 | COST |  |  | 0 | 86000
15 16 | EXCAVATE PLANT WAREHOUSE | 2 | 1 | OP |  |  | 5 | 0
16 17 | POUR PILE CAPS P-W | 2 | 3 | COST |  |  | 0 | 50000
16 17 | POUR PILE CAPS P-W | 2 | 3 | CP |  |  | 4 | 0
16 17 | POUR PILE CAPS P-W | 2 | 3 | LB |  |  | 20 | 0
17 18 | FORM AND POUR GRADE BEAMS P-W | 2 | 3 | COST |  |  | 0 | 70000
17 18 | FORM AND POUR GRADE BEAMS P-W | 2 | 3 | CP |  |  | 2 | 0
17 18 | FORM AND POUR GRADE BEAMS P-W | 2 | 3 | LB |  |  | 2 | 0
18 19 | BACKFILL AND COMPACT P-W | 2 | 1 | COST |  |  | 0 | 9000
18 19 | BACKFILL AND COMPACT P-W | 2 | 1 | OP |  |  | 5 | 0
18 21 | FORM AND POUR RAILROAD LOADING DOCK P-W | 2 | 3 | COST |  |  | 0 | 15000
18 21 | FORM AND POUR RAILROAD LOADING DOCK P-W | 2 | 3 | CP |  |  | 4 | 0
18 21 | FORM AND POUR RAILROAD LOADING DOCK P-W | 2 | 3 | LB |  |  | 2 | 0
18 22 | FORM AND POUR TRUCK LOADING DOCK P-W | 2 | 3 | COST |  |  | 0 | 15000
18 22 | FORM AND POUR TRUCK LOADING DOCK P-W | 2 | 3 | CP |  |  | 4 | 0
18 22 | FORM AND POUR TRUCK LOADING DOCK P-W | 2 | 3 | LB |  |  | 2 | 0
19 20 | UNDERSLAB PLUMBING P-W | 2 | 5 | COST |  |  | 0 | 12000
19 20 | UNDERSLAB PLUMBING P-W | 2 | 5 | PB |  |  | 4 | 0
20 22 | UNDERSLAB CONDUIT P-W | 2 | 4 | COST |  |  | 0 | 7500
20 22 | UNDERSLAB CONDUIT P-W | 2 | 4 | EL |  |  | 6 | 0
21 22 | [6 empty] | 0 | 0
22 29 | FORM AND POUR SLABS P-W | 2 | 3 | COST |  |  | 0 | 225000
22 29 | FORM AND POUR SLABS P-W | 2 | 3 | CP |  |  | 4 | 0
22 29 | FORM AND POUR SLABS P-W | 2 | 3 | LB |  |  | 2 | 0
23 24 | SPREAD FOOTINGS OFFICE | 2 | 3 | COST |  |  | 0 | 17500
23 24 | SPREAD FOOTINGS OFFICE | 2 | 3 | CP |  |  | 4 | 0
23 24 | SPREAD FOOTINGS OFFICE | 2 | 3 | LB |  |  | 2 | 0
24 25 | FORM AND POUR GRADE BEAMS OFFICE | 2 | 3 | COST |  |  | 0 | 21000
24 25 | FORM AND POUR GRADE BEAMS OFFICE | 2 | 3 | CP |  |  | 4 | 0
24 25 | FORM AND POUR GRADE BEAMS OFFICE | 2 | 3 | LB |  |  | 2 | 0
25 26 | BACKFILL AND COMPACT OFFICE | 2 | 1 | COST |  |  | 0 | 1800
25 26 | BACKFILL AND COMPACT OFFICE | 2 | 1 | OP |  |  | 5 | 0
26 27 | UNDERSLAB PLUMBING OFFICE | 2 | 5 | COST |  |  | 0 | 9000
26 27 | UNDERSLAB PLUMBING OFFICE | 2 | 5 | PB |  |  | 4 | 0
27 28 | UNDERSLAB CONDUIT OFFICE | 2 | 4 | COST |  |  | 0 | 5000
27 28 | UNDERSLAB CONDUIT OFFICE | 2 | 4 | CP |  |  | 4 | 0
27 28 | UNDERSLAB CONDUIT OFFICE | 2 | 4 | LB |  |  | 2 | 0
28 99 | FORM AND POUR SLABS OFFICE | 2 | 3 | COST |  |  | 0 | 18000
28 99 | FORM AND POUR SLABS OFFICE | 2 | 3 | CP |  |  | 4 | 0
28 99 | FORM AND POUR SLABS OFFICE | 2 | 3 | LB |  |  | 2 | 0
29 30 | ERECT STRUCTURAL STEEL P-W | 3 | 6 | COST |  |  | 0 | 50000
29 30 | ERECT STRUCTURAL STEEL P-W | 3 | 6 | OP |  |  | 2 | 0
29 30 | ERECT STRUCTURAL STEEL P-W | 3 | 6 | IW |  |  | 6 | 0
30 31 | PLUMB AND BOLT STEEL P-W | 3 | 6 | COST |  |  | 0 | 15000
30 31 | PLUMB AND BOLT STEEL P-W | 3 | 6 | OP |  |  | 2 | 0
30 31 | PLUMB AND BOLT STEEL P-W | 3 | 6 | IW |  |  | 6 | 0
31 32 | ERECT CRANEWAY AND CRANE P-W | 3 | 6 | COST |  |  | 0 | 20000
31 32 | ERECT CRANEWAY AND CRANE P-W | 3 | 6 | IW |  |  | 4 | 0
31 33 | ERECT MONORAIL TRACK P-W | 3 | 6 | COST |  |  | 0 | 10000
31 33 | ERECT MONORAIL TRACK P-W | 3 | 6 | IW |  |  | 4 | 0
32 33 | [6 empty] | 0 | 0
33 34 | ERECT BAR JOISTS P-W | 3 | 6 | COST |  |  | 0 | 15000
33 34 | ERECT BAR JOISTS P-W | 3 | 6 | OP |  |  | 2 | 0
33 34 | ERECT BAR JOISTS P-W | 3 | 6 | IW |  |  | 6 | 0
34 35 | ERECT ROOF PLANKS P-W | 3 | 7 | COST |  |  | 0 | 15000
34 35 | ERECT ROOF PLANKS P-W | 3 | 7 | LB |  |  | 2 | 0
34 35 | ERECT ROOF PLANKS P-W | 3 | 7 | OP |  |  | 2 | 0
34 35 | ERECT ROOF PLANKS P-W | 3 | 7 | CP |  |  | 2 | 0
35 36 | ERECT SIDING P-W | 3 | 12 | COST |  |  | 0 | 75000
35 36 | ERECT SIDING P-W | 3 | 12 | OP |  |  | 2 | 0
35 36 | ERECT SIDING P-W | 3 | 12 | IW |  |  | 6 | 0
35 37 | BUILT-UP ROOFING P-W | 3 | 13 | COST |  |  | 0 | 175000
35 37 | BUILT-UP ROOFING P-W | 3 | 13 | RF |  |  | 8 | 0
36 37 | [6 empty] | 0 | 0
37 80 | PERIMETER FENCE | 5 | 15 | COST |  |  | 0 | 25000
37 80 | PERIMETER FENCE | 5 | 15 | LB |  |  | 6 | 0
37 90 | PAVE PARKING AREA | 5 | 16 | COST |  |  | 0 | 35000
37 90 | PAVE PARKING AREA | 5 | 16 | OP |  |  | 4 | 0
37 90 | PAVE PARKING AREA | 5 | 16 | LB |  |  | 6 | 0
37 91 | GRADE AND BALLAST RAILROAD SIDING | 5 | 17 | COST |  |  | 0 | 20000
37 91 | GRADE AND BALLAST RAILROAD SIDING | 5 | 17 | OP |  |  | 2 | 0
37 91 | GRADE AND BALLAST RAILROAD SIDING | 5 | 17 | LB |  |  | 6 | 0
37 92 | ACCESS ROAD | 5 | 16 | COST |  |  | 0 | 25000
37 92 | ACCESS ROAD | 5 | 16 | OP |  |  | 4 | 0
37 92 | ACCESS ROAD | 5 | 16 | LB |  |  | 6 | 0
37 93 | AREA LIGHTING | 5 | 4 | COST |  |  | 0 | 33000
37 93 | AREA LIGHTING | 5 | 4 | EL |  |  | 4 | 0
37 300 | [6 empty] | 0 | 0
37 301 | [6 empty] | 0 | 0
37 302 | [6 empty] | 0 | 0
37 303 | [6 empty] | 0 | 0
37 304 | [6 empty] | 0 | 0
37 305 | [6 empty] | 0 | 0
37 306 | [6 empty] | 0 | 0
37 307 | [6 empty] | 0 | 0
37 308 | [6 empty] | 0 | 0
38 43 | INSTALL POWER CONDUIT P-W | 3 | 4 | COST |  |  | 0 | 21000
38 43 | INSTALL POWER CONDUIT P-W | 3 | 4 | EL |  |  | 6 | 0
39 42 | FRAME CEILING P-W | 3 | 18 | COST |  |  | 0 | 25000
39 42 | FRAME CEILING P-W | 3 | 18 | CP |  |  | 6 | 0
39 42 | FRAME CEILING P-W | 3 | 18 | LB |  |  | 2 | 0
40 47 | TEST PIPING SYSTEMS P-W | 3 | 8 | COST |  |  | 0 | 5000
40 47 | TEST PIPING SYSTEMS P-W | 3 | 8 | PF |  |  | 4 | 0
41 47 | PREOPERATIONAL CHECK | 3 | 8 | COST |  |  | 0 | 2000
41 47 | PREOPERATIONAL CHECK | 3 | 8 | ST |  |  | 2 | 0
42 44 | DRYWALL PARTITIONS P-W | 3 | 19 | COST |  |  | 0 | 35000
42 44 | DRYWALL PARTITIONS P-W | 3 | 19 | CP |  |  | 6 | 0
42 44 | DRYWALL PARTITIONS P-W | 3 | 19 | LB |  |  | 2 | 0
43 49 | INSTALL BRANCH CONDUIT P-W | 3 | 4 | COST |  |  | 0 | 29000
43 49 | INSTALL BRANCH CONDUIT P-W | 3 | 4 | EL |  |  | 6 | 0
44 45 | [6 empty] | 0 | 0
44 46 | [6 empty] | 0 | 0
44 48 | CERAMIC TILE | 3 | 20 | COST |  |  | 0 | 10000
44 58 | HANG INTERIOR DOORS P-W | 3 | 21 | COST |  |  | 0 | 20000
44 58 | HANG INTERIOR DOORS P-W | 3 | 21 | CP |  |  | 2 | 0
44 58 | HANG INTERIOR DOORS P-W | 3 | 21 | LB |  |  | 2 | 0
45 51 | ROOM OUTLETS P-W | 3 | 4 | COST |  |  | 0 | 16500
45 51 | ROOM OUTLETS P-W | 3 | 4 | EL |  |  | 6 | 0
46 52 | INSTALL DUCTWORK P-W | 3 | 8 | COST |  |  | 0 | 25000
46 52 | INSTALL DUCTWORK P-W | 3 | 8 | SM |  |  | 4 | 0
47 58 | LIGHT OFF BOILER AND TEST | 3 | 8 | COST |  |  | 0 | 1500
47 58 | LIGHT OFF BOILER AND TEST | 3 | 8 | ST |  |  | 2 | 0
48 53 | PAINT ROOMS P-W | 3 | 22 | COST |  |  | 0 | 15000
48 53 | PAINT ROOMS P-W | 3 | 22 | PA |  |  | 10 | 0
49 45 | [6 empty] | 0 | 0
49 50 | PULL WIRE P-W | 3 | 4 | COST |  |  | 0 | 38000
49 50 | PULL WIRE P-W | 3 | 4 | EL |  |  | 6 | 0
50 54 | INSTALL PANEL INTERNALS P-W | 3 | 4 | COST |  |  | 0 | 7500
50 54 | INSTALL PANEL INTERNALS P-W | 3 | 4 | EL |  |  | 4 | 0
51 56 | INSTALL ELECTRICAL FIXTURES | 3 | 4 | COST |  |  | 0 | 31000
51 56 | INSTALL ELECTRICAL FIXTURES | 3 | 4 | EL |  |  | 6 | 0
52 58 | INSULATE HEATING AND VENTILATING SYSTEM P-W | 3 | 8 | COST |  |  | 0 | 10000
52 58 | INSULATE HEATING AND VENTILATING SYSTEM P-W | 3 | 8 | IN |  |  | 6 | 0
53 57 | FLOOR TILE P-W | 3 | 22 | COST |  |  | 0 | 20000
53 57 | FLOOR TILE P-W | 3 | 22 | TL |  |  | 8 | 0
53 58 | INSTALL PLUMBING FIXTURES P-W | 3 | 5 | COST |  |  | 0 | 20000
53 58 | INSTALL PLUMBING FIXTURES P-W | 3 | 5 | PB |  |  | 4 | 0
54 55 | TERMINATE WIRE P-W | 3 | 4 | COST |  |  | 0 | 7500
54 55 | TERMINATE WIRE P-W | 3 | 4 | EL |  |  | 4 | 0
55 56 | RING OUT P-W | 3 | 4 | COST |  |  | 0 | 5000
55 56 | RING OUT P-W | 3 | 4 | EL |  |  | 4 | 0
56 58 | ENERGIZE POWER | 3 | 4 | COST |  |  | 0 | 2000
56 58 | ENERGIZE POWER | 3 | 4 | EL |  |  | 2 | 0
57 58 | INSTALL FURNISHINGS P-W | 3 | 24 | COST |  |  | 0 | 30000
57 58 | INSTALL FURNISHINGS P-W | 3 | 24 | LB |  |  | 6 | 0
58 80 | ERECT FLAGPOLE | 5 | 29 | COST |  |  | 0 | 1500
58 80 | ERECT FLAGPOLE | 5 | 29 | LB |  |  | 2 | 0
58 94 | FINE GRADE | 5 | 1 | COST |  |  | 0 | 5000
58 94 | FINE GRADE | 5 | 1 | OP |  |  | 2 | 0
59 60 | ERECT PRECAST ROOF OFFICE | 4 | 7 | COST |  |  | 0 | 30000
59 60 | ERECT PRECAST ROOF OFFICE | 4 | 7 | OP |  |  | 1 | 0
59 60 | ERECT PRECAST ROOF OFFICE | 4 | 7 | CP |  |  | 2 | 0
59 60 | ERECT PRECAST ROOF OFFICE | 4 | 7 | LB |  |  | 2 | 0
60 61 | EXTERIOR MASONRY OFFICE | 4 | 14 | COST |  |  | 0 | 380000
60 61 | EXTERIOR MASONRY OFFICE | 4 | 14 | MA |  |  | 10 | 0
60 76 | INSTALL PACKAGE AIR CONDITIONING | 4 | 8 | COST |  |  | 0 | 40000
60 76 | INSTALL PACKAGE AIR CONDITIONING | 4 | 8 | ST |  |  | 2 | 0
61 62 | EXTERIOR DOORS OFFICE | 4 | 21 | COST |  |  | 0 | 3600
61 62 | EXTERIOR DOORS OFFICE | 4 | 21 | CP |  |  | 1 | 0
61 62 | EXTERIOR DOORS OFFICE | 4 | 21 | LB |  |  | 1 | 0
61 63 | PLACE SINGLE-PLY ROOFING OFFICE | 4 | 17 | COST |  |  | 0 | 32000
61 63 | PLACE SINGLE-PLY ROOFING OFFICE | 4 | 17 | RF |  |  | 8 | 0
61 64 | INSTALL PIPING OFFICE | 4 | 8 | COST |  |  | 0 | 9000
61 64 | INSTALL PIPING OFFICE | 4 | 8 | PF |  |  | 4 | 0
61 65 | INSTALL BACKING BOXES | 4 | 4 | COST |  |  | 0 | 4000
61 65 | INSTALL BACKING BOXES | 4 | 4 | EL |  |  | 4 | 0
61 68 | GLAZE OFFICE | 4 | 25 | COST |  |  | 0 | 12000
61 68 | GLAZE OFFICE | 4 | 25 | GZ |  |  | 8 | 0
61 77 | DUCTWORK OFFICE | 4 | 8 | COST |  |  | 0 | 16000
61 77 | DUCTWORK OFFICE | 4 | 8 | SM |  |  | 4 | 0
62 63 | [6 empty] | 0 | 0
63 68 | [6 empty] | 0 | 0
63 80 | PAINT EXTERIOR OFFICE | 4 | 22 | COST |  |  | 0 | 6000
63 80 | PAINT EXTERIOR OFFICE | 4 | 22 | PA |  |  | 8 | 0
64 67 | TEST PIPING OFFICE | 4 | 8 | COST |  |  | 0 | 1000
64 67 | TEST PIPING OFFICE | 4 | 8 | PF |  |  | 2 | 0
65 66 | INSTALL CONDUIT OFFICE | 4 | 4 | COST |  |  | 0 | 9000
65 66 | INSTALL CONDUIT OFFICE | 4 | 4 | EL |  |  | 6 | 0
66 67 | [6 empty] | 0 | 0
66 74 | PULL WIRE OFFICE | 4 | 4 | COST |  |  | 0 | 10000
66 74 | PULL WIRE OFFICE | 4 | 4 | EL |  |  | 6 | 0
67 68 | METAL STUDS OFFICE | 4 | 19 | COST |  |  | 0 | 5000
67 68 | METAL STUDS OFFICE | 4 | 19 | CP |  |  | 10 | 0
67 68 | METAL STUDS OFFICE | 4 | 19 | LB |  |  | 10 | 0
68 69 | DRYWALL | 4 | 19 | COST |  |  | 0 | 5000
68 69 | DRYWALL | 4 | 19 | CP |  |  | 5 | 0
68 69 | DRYWALL | 4 | 19 | LB |  |  | 5 | 0
69 70 | DRYWALL | 4 | 19 | COST |  |  | 0 | 10000
69 70 | DRYWALL | 4 | 19 | CP |  |  | 5 | 0
69 70 | DRYWALL | 4 | 19 | LB |  |  | 5 | 0
69 73 | CERAMIC TILE OFFICE | 4 | 20 | COST |  |  | 0 | 9000
69 73 | CERAMIC TILE OFFICE | 4 | 20 | TL |  |  | 6 | 0
70 71 | WOOD TRIM OFFICE | 4 | 26 | COST |  |  | 0 | 12000
70 71 | WOOD TRIM OFFICE | 4 | 26 | CP |  |  | 4 | 0
70 77 | [6 empty] | 0 | 0
71 72 | PAINT INTERIOR OFFICE | 4 | 22 | COST |  |  | 0 | 16000
71 72 | PAINT INTERIOR OFFICE | 4 | 22 | PA |  |  | 10 | 0
71 80 | HANG DOORS OFFICE | 4 | 21 | COST |  |  | 0 | 10000
71 80 | HANG DOORS OFFICE | 4 | 21 | CP |  |  | 4 | 0
71 80 | HANG DOORS OFFICE | 4 | 21 | LB |  |  | 4 | 0
72 73 | [6 empty] | 0 | 0
72 78 | [6 empty] | 0 | 0
72 80 | FLOOR TILE OFFICE | 4 | 20 | COST |  |  | 0 | 18000
72 80 | FLOOR TILE OFFICE | 4 | 20 | TL |  |  | 6 | 0
73 80 | TOILET FIXTURES OFFICE | 4 | 5 | COST |  |  | 0 | 10000
73 80 | TOILET FIXTURES OFFICE | 4 | 5 | PB |  |  | 4 | 0
74 75 | INSTALL PANEL INTERNALS OFFICE | 5 | 4 | COST |  |  | 0 | 5000
74 75 | INSTALL PANEL INTERNALS OFFICE | 5 | 4 | EL |  |  | 6 | 0
74 76 | [6 empty] | 0 | 0
75 79 | TERMINATE WIRES OFFICE | 4 | 4 | COST |  |  | 0 | 7500
75 79 | TERMINATE WIRES OFFICE | 4 | 4 | EL |  |  | 6 | 0
76 79 | A/C ELECTRICAL CONNECTIONS | 4 | 4 | COST |  |  | 0 | 2000
76 79 | A/C ELECTRICAL CONNECTIONS | 4 | 4 | EL |  |  | 4 | 0
77 78 | INSTALL CEILING GRID OFFICE | 4 | 18 | COST |  |  | 0 | 10000
77 78 | INSTALL CEILING GRID OFFICE | 4 | 18 | CP |  |  | 4 | 0
77 78 | INSTALL CEILING GRID OFFICE | 4 | 18 | LB |  |  | 4 | 0
78 80 | ACOUSTIC TILES OFFICE | 4 | 18 | COST |  |  | 0 | 20000
78 80 | ACOUSTIC TILES OFFICE | 4 | 18 | CP |  |  | 2 | 0
78 80 | ACOUSTIC TILES OFFICE | 4 | 18 | LB |  |  | 2 | 0
79 80 | RING OUT | 4 | 4 | COST |  |  | 0 | 2500
79 80 | RING OUT | 4 | 4 | EL |  |  | 2 | 0
90 58 | [6 empty] | 0 | 0
91 58 | INSTALL RAILROAD SIDING | 5 | 17 | COST |  |  | 0 | 50000
91 58 | INSTALL RAILROAD SIDING | 5 | 17 | OP |  |  | 2 | 0
91 58 | INSTALL RAILROAD SIDING | 5 | 17 | LB |  |  | 6 | 0
92 58 | [6 empty] | 0 | 0
93 80 | [6 empty] | 0 | 0
94 80 | SEED AND PLANT | 5 | 27 | COST |  |  | 0 | 20000
94 80 | SEED AND PLANT | 5 | 27 | LB |  |  | 6 | 0
99 59 | ERECT PRECAST STRUCTURE | 4 | 7 | COST |  |  | 0 | 20000
99 59 | ERECT PRECAST STRUCTURE | 4 | 7 | OP |  |  | 1 | 0
99 59 | ERECT PRECAST STRUCTURE | 4 | 7 | CP |  |  | 2 | 0
99 59 | ERECT PRECAST STRUCTURE | 4 | 7 | LB |  |  | 2 | 0
210 211 | APPROVE FOUNDATION REBAR | [5 empty] | 0 | 0
211 16 | FAB/DEL FOUNDATION REBAR | [5 empty] | 0 | 0
212 213 | APPROVE STRUCTURAL STEEL | [5 empty] | 0 | 0
213 23 | FAB/DEL STRUCTURAL STEEL |  |  | COST |  |  | 0 | 550000
214 215 | APPROVE CRANE | [5 empty] | 0 | 0
215 31 | FAB/DEL CRANE |  |  | COST |  |  | 0 | 180000
216 217 | APPROVE BAR JOISTS | [5 empty] | 0 | 0
217 33 | FAB/DEL BAR JOISTS |  |  | COST |  |  | 0 | 60000
218 219 | APPROVE SIDING | [5 empty] | 0 | 0
219 35 | FAB/DEL SIDING |  |  | COST |  |  | 0 | 300000
220 221 | APPROVE PLANT ELECTRICAL LOAD CENTER | [5 empty] | 0 | 0
221 300 | FAB/DEL PLANT ELECTRICAL LOAD CENTER | [5 empty] | 0 | 0
222 223 | APPROVE POWER PANELS - PLANT | [5 empty] | 0 | 0
223 301 | FAB/DEL POWER PANELS - PLANT | [5 empty] | 0 | 0
224 225 | APPROVE EXTERIOR DOORS | [5 empty] | 0 | 0
225 226 | APPROVE PLANT ELECTRICAL FIXTURES |  |  | COST |  |  | 0 | 60000
225 302 | FAB/DEL EXTERIOR DOORS | [5 empty] | 0 | 0
226 51 | FAB/DEL PLANT ELECTRICAL FIXTURES | [5 empty] | 0 | 0
227 228 | APPROVE PLANT HEATING AND VENTILATING FANS | [5 empty] | 0 | 0
228 304 | FAB/DEL PLANT HEATING AND VENTILATING FANS | [5 empty] | 0 | 0
229 230 | APPROVE BOILER | [5 empty] | 0 | 0
230 306 | FAB/DEL BOILER | [5 empty] | 0 | 0
231 232 | APPROVE OIL TANK | [5 empty] | 0 | 0
232 305 | FAB/DEL OIL TANK | [5 empty] | 0 | 0
233 234 | APPROVE PRECAST | [5 empty] | 0 | 0
234 99 | FAB/DEL PRECAST |  |  | COST |  |  | 0 | 70000
235 236 | APPROVE PACKAGED A/C | [5 empty] | 0 | 0
236 60 | FAB/DEL PACKAGED A/C | [5 empty] | 0 | 0
300 38 | SET ELECTRICAL LOAD CENTER | 3 | 4 | COST |  |  | 0 | 30500
300 38 | SET ELECTRICAL LOAD CENTER | 3 | 4 | EL |  |  | 4 | 0
301 43 | INSTALL POWER PANEL BACKING BOXES | 3 | 4 | COST |  |  | 0 | 18000
301 43 | INSTALL POWER PANEL BACKING BOXES | 3 | 4 | EL |  |  | 6 | 0
302 42 | EXTERIOR DOORS P-W | 3 | 6 | COST |  |  | 0 | 30000
302 42 | EXTERIOR DOORS P-W | 3 | 6 | CP |  |  | 2 | 0
302 42 | EXTERIOR DOORS P-W | 3 | 6 | LB |  |  | 2 | 0
303 39 | MASONRY PARTITIONS | 3 | 14 | COST |  |  | 0 | 80000
303 39 | MASONRY PARTITIONS | 3 | 14 | MA |  |  | 10 | 0
304 46 | INSTALL HEATING AND VENTILATING UNITS | 3 | 8 | COST |  |  | 0 | 120000
304 46 | INSTALL HEATING AND VENTILATING UNITS | 3 | 8 | ST |  |  | 8 | 0
305 47 | INSTALL FUEL OIL TANK | 3 | 8 | COST |  |  | 0 | 15000
305 47 | INSTALL FUEL OIL TANK | 3 | 8 | ST |  |  | 4 | 0
306 41 | ERECT BOILERS AND AUXILIARIES | 3 | 8 | COST |  |  | 0 | 25000
306 41 | ERECT BOILERS AND AUXILIARIES | 3 | 8 | ST |  |  | 4 | 0
307 40 | FABRICATE PIPING SYSTEMS | 3 | 8 | COST |  |  | 0 | 60000
308 58 | INSTALL MONORAIL | 3 | 6 | COST |  |  | 0 | 25000
308 58 | INSTALL MONORAIL | 3 | 6 | IW |  |  | 4 | 0