## Slide 1
2025 Construction CPM Conference Benchmarking As-Built Lags
Ron Winter, PSP, FAACE
Schedule Analyzer Software

## Slide 2: Ron Winter, PSP, FAACE
Bachelor of Science in Engineering
Construction Scheduler
US Air Force Navigator
Construction Scheduler
Master of Science in Systems Management
Programmer, Project Manager, Customer Support, and Industrial Trainer
Construction Scheduler
Developer of Schedule Analyzer Software

## Slide 3: What To Expect
Reporting relationship performance
The anatomy of a relationship
Relationship float consumption
Measuring relationship progress
Benchmarking relationship progress
Future of relationship tracking

## Slide 4
2025 Construction CPM Conference Reporting Relationship Performance

## Slide 5: Evolution of CPM Software
In the beginning there was ADM
  Arrow Diagramming Method
ADM does not have relationships*
  Relationships built-into activity IDs
    Act 100-110 predecessor to Act 110-120
  No need for a relationship report
  Lags in PDM were just another ADM activity
    Easy to benchmark ‘relationships’
    Example, “Was concrete curing time observed?”

## Slide 6: Evolution of CPM Software
Then came PDM
  Precedence Diagramming Method
Logic represented by separate relationships
  Planned versus actual lags difficult to see
    Example, “Was concrete curing time sufficient?”
  No relationship variance reports
  Perhaps software companies ‘forgot’ to add this?

## Slide 7: Obvious Missing Feature
Status of the remaining (in-progress) lag
  We know this for activities
  Why not for relationships?
Updating status of remaining lag
  Huh? Who does that?
  No one
Instead of SNET constraint on successor
  Why not update lag?

## Slide 8
2025 Construction CPM Conference Anatomy of a Relationship

## Slide 9: Requirements to Begin
Completion of logical predecessors
Administrative requirements
  Access to the work area
  Enough qualified workers present
  Supervision
  Usable plans
  Required materials and tools being present
  Availability of required utilities

## Slide 10: As-Built Relationship
Variance

## Slide 11: Relationship Properties
You can’t manage what you can’t measure
With existing software
  We can’t measure relationships
  What is there to measure?

## Slide 12: Rels & Activity Similarities
Both have duration
  Relationship lag/activity remaining duration
  May be expended non-linearly
Both have float
  May be different
  P6 shows relationship float on predecessor tab
Relationships do not consume resources
  Except for time (and float)

## Slide 13
2025 Construction CPM Conference Relationship Float Consumption

## Slide 14: Rel Float Consumption
Relationship does not need to start on-time
  If there is float available
Monitoring float consumption involves
  Monitoring activity durations
  Monitoring relationship durations
Relationship As-Built Report

## Slide 15: Rel As-Built Report
----------Lag Duration---------- Lost
Pred C Float Succ C Float Type Planned Actual Remaing Variance Float
—————— - ——————— —————— - ——————— —— ——————— ——————— ——————— ——————— ———————
A1000 Y -76 A9050 N -19 FS 0 0 0 0 -57
A1000 Y -76 EW003 N 140 FS 0 163 0 163 -216
A1000 Y -76 A9630 N 144 FS 0 196 0 196 -220
A1000 Y -76 A8250 N 113 FS 0 0 0 0 -189
A1000 Y -76 A1200 N 83 FS 0 0 0 0 -159
A1000 Y -76 A1380 Y -54 FS 0 0 0 0 -22
A1000 Y -76 A1050 N 73 FS 0 0 0 0 -149
A1000 Y -76 A2460 N 82 FS 0 126 0 126 -158
A1000 Y -76 A7550 N 117 FS 0 84 0 84 -193
A1050 N 73 A1070 N 73 FS 0 0 0 0 0
A1070 N 73 A1080 N 73 FS 0 -1 0 -1 0
A1850 Y -54 A9830 Y -56 FS 0 19.6 0 19.6 2 *
A10930 N 2 A10950 N FS 0 13 0 13
… … …
—————— - ——————— —————— - ——————— —— ——————— ——————— ——————— ——————— ———————
425 total relationships with actual progress were analyzed.
CAUTION: Lines ending with a '*' indicate that the relationship was critical
and the lag delay caused it to lose (positive) float.

## Slide 16: As-Built Float
Difficult to report
Once activity is complete
  Float value not useful
Look-up activity float in baseline schedules
Critical relationship
  Predecessor activity critical and
  Successor activity critical
  Alternatively; when relationship is critical
    No one reports on this

## Slide 17
2025 Construction CPM Conference Measuring Relationship Progress

## Slide 18: Measuring Relationships
As-Planned versus As-Built lag durations
Can be benchmarked just like activities
Relationship Actual Duration Quality Statistics
  Need to define what is ‘on-time’
  The following examples use less that one day
  (-0.9999 to +0.9999)
Four new reports

## Slide 19: Summary Rel Analysis
All Relationships
Total relationships analyzed : 1484
Total relationships with actual progress : 425
Mean of the lag variance : 10
Standard Deviation of lag variance : 32.57
Number of early relationships : 22
Percent of early relationships : 5.18%
Number of on-time relationships : 236
Percent of on-time relationships : 55.53%
Number of late relationships : 167
Percent of late relationships : 39.29%
Just Critical Relationships
Total critical relationships : 53
Mean of critical lag variance : 1
Standard Deviation critical lag variance : 7.39
Number of early critical relationships : 6
Percent of early critical rels : 11.32%
Number of on-time critical relationships : 29
Percent of on-time critical rels : 54.72%
Number of late critical relationships : 18
Percent of late critical rels : 33.96%
Number critical lag delays with progress : 3

## Slide 20: Lag Analysis
Does planned lag value affect accuracy?
  Example
Planned Number Average Number Percent Number Percent Number Percent
Lag-Val of-Lags Actual On-Time On-Time Early Early Late Late
——————— ——————— ——————— ——————— ——————— ——————— ——————— ——————— ———————
0 725 31 115 15.86 149 20.55 461 63.59
1 32 21 0 0 1 3.12 31 96.88
2 3 9 0 0 0 0 3 100
5 8 3 2 25 4 50 2 25
10 1 2 0 0 1 100 0 0
65 1 65 1 100 0 0 0 0
——————— ——————— ——————— ——————— ——————— ——————— ——————— ——————— ———————

## Slide 21: Responsibility Analysis
Breakdown by successor responsibility
Planned Number Average Number Percent Number Percent Number Percent
Act Code Lag-Val of-Lags Actual On-Time On-Time Early Early Late Late
—————————— ——————— ——————— ——————— ——————— ——————— ——————— ——————— ——————— ———————
Client 0 100 1 25 25 3 3 72 72
Contractor 0 325 34 66 20.31 48 14.77 211 64.92
Designer 0 217 20 64 29.49 8 3.69 145 66.82
Supplier 0 61 7 11 18.03 3 4.92 47 77.05
Contractor 1 1 4 0 0 0 0 1 100
Contractor 2 1 2 1 100 0 0 0 0
Designer 4 4 22 0 0 1 25 3 75
Contractor 4 3 3 0 0 1 33.33 2 66.67
Contractor 5 3 8 0 0 0 0 3 100
Contractor 8 5 52 0 0 1 20 4 80
Supplier 8 1 32 0 0 0 0 1 100
Contractor 11 1 88 0 0 0 0 1 100
Contractor 12 2 52 0 0 0 0 2 100
Supplier 15 1 28 0 0 0 0 1 100
Supplier 16 1 28 0 0 0 0 1 100
Contractor 22 1 20 0 0 1 100 0 0
Contractor 24 1 152 0 0 0 0 1 100
—————————— ——————— ——————— ——————— ——————— ——————— ——————— ——————— ——————— ———————

## Slide 22: Lag Graphical Analysis

## Slide 23
2025 Construction CPM Conference Benchmarking Relationship Progress

## Slide 24: Benchmark Study
 |  |  |  | Early |  | On-Time |  | Late | 
Schedule Name | Started Rels | Ave Lag Variance | St. Dev Variance | Total | Percent | Total | Percent | Total | Percent
EKR2 | 41 | -2 | 12 | 24 | 59% | 12 | 29% | 5 | 12%
PL03 | 77 | -1 | 33 | 23 | 30% | 19 | 25% | 35 | 45%
HQNE | 146 | 0 | 13 | 54 | 37% | 29 | 20% | 63 | 43%
PARK | 152 | 2 | 8 | 15 | 10% | 51 | 34% | 86 | 57%
TR11 | 128 | 3 | 27 | 35 | 27% | 29 | 23% | 64 | 50%
SP10 | 78 | 5 | 13 | 6 | 8% | 17 | 22% | 55 | 71%
0009 | 216 | 8 | 16 | 15 | 7% | 46 | 21% | 155 | 72%
SA11 | 954 | 8 | 88 | 279 | 29% | 85 | 9% | 590 | 62%
UP12 | 638 | 9 | 42 | 71 | 11% | 187 | 29% | 380 | 60%
6800 | 425 | 10 | 33 | 22 | 5% | 236 | 56% | 167 | 39%
COUR | 6021 | 10 | 45 | 998 | 17% | 967 | 16% | 4056 | 67%
VOGL | 96 | 11 | 30 | 9 | 9% | 41 | 43% | 46 | 48%
CPWT | 1204 | 12 | 149 | 422 | 35% | 202 | 17% | 580 | 48%
POLB | 269 | 12 | 41 | 64 | 24% | 29 | 11% | 176 | 65%
OMVP | 643 | 13 | 89 | 195 | 30% | 32 | 5% | 416 | 65%
0755 | 1940 | 14 | 63 | 697 | 36% | 113 | 6% | 1130 | 58%
CHOP | 10808 | 14 | 68 | 2998 | 28% | 1841 | 17% | 5969 | 55%
MULE | 7244 | 14 | 36 | 740 | 10% | 2092 | 29% | 4412 | 61%
HQNG | 5311 | 16 | 37 | 394 | 7% | 1524 | 29% | 3393 | 64%
WTPR | 731 | 17 | 88 | 185 | 25% | 87 | 12% | 459 | 63%
7031 | 676 | 18 | 41 | 69 | 10% | 144 | 21% | 463 | 68%
JG09 | 526 | 19 | 38 | 95 | 38% | 42 | 8% | 389 | 74%
C001 | 92 | 20 | 26 | 11 | 12% | 17 | 18% | 64 | 70%

## Slide 25: Benchmark Study
PS43 | 7644 | 21 | 91 | 2638 | 35% | 753 | 10% | 4253 | 56%
SHTE | 1161 | 21 | 41 | 145 | 12% | 222 | 19% | 794 | 68%
2W52 | 4672 | 23 | 107 | 1468 | 31% | 561 | 12% | 2643 | 57%
HYD4 | 728 | 23 | 54 | 66 | 9% | 167 | 23% | 495 | 68%
0575 | 203 | 28 | 72 | 16 | 8% | 82 | 40% | 105 | 52%
1134 | 5101 | 30 | 55 | 527 | 10% | 709 | 14% | 3865 | 76%
A031 | 770 | 31 | 97 | 155 | 20% | 118 | 15% | 497 | 65%
CU38 | 15234 | 31 | 61 | 2688 | 18% | 1883 | 12% | 10663 | 70%
HWY2 | 5915 | 32 | 73 | 840 | 14% | 1318 | 22% | 3757 | 64%
1501 | 7513 | 35 | 98 | 1020 | 14% | 1748 | 23% | 4745 | 63%
HQNS | 945 | 35 | 63 | 95 | 10% | 166 | 18% | 684 | 72%
3332 | 972 | 37 | 88 | 185 | 19% | 162 | 17% | 625 | 65%
2827 | 6133 | 42 | 128 | 1149 | 19% | 1043 | 17% | 3941 | 64%
X101 | 2943 | 44 | 94 | 390 | 13% | 380 | 13% | 2173 | 74%
VERY | 21270 | 45 | 97 | 2149 | 10% | 6087 | 29% | 13034 | 61%
S053 | 5066 | 47 | 83 | 192 | 4% | 2231 | 44% | 2643 | 52%
RT58 | 385 | 49 | 106 | 47 | 12% | 46 | 12% | 292 | 76%
B114 | 2147 | 52 | 192 | 334 | 16% | 522 | 24% | 1291 | 60%
X042 | 1641 | 52 | 161 | 208 | 13% | 321 | 20% | 1112 | 68%
BT29 | 1201 | 58 | 160 | 248 | 21% | 223 | 19% | 730 | 61%
0813 | 1185 | 61 | 213 | 376 | 32% | 131 | 11% | 678 | 57%
0354 | 14281 | 93 | 273 | 1339 | 9% | 3610 | 25% | 9332 | 65%
PLPB | 1522 | 95 | 202 | 314 | 21% | 70 | 5% | 1138 | 75%
Mean |  | 26 |  |  | 19% |  | 20% |  | 61%
St. Dev. |  | 22 |  |  | 12% |  | 11% |  | 12%
Totals: 46 | 147048 |  |  | 24010 |  | 30395 |  | 92643 | 
Early
On-Time
Late
Average

## Slide 26: Benchmarking Relationships
46 independent schedules analyzed
  Mean lag variance: 26 days
  Standard deviation: 22 days
Benchmark study of as-built relationships
  Schedules with mean variance greater than 48 days are out of the normal
  7 schedules failed this benchmark

## Slide 27: Benchmarking Relationships
46 independent as-built schedules analyzed
  19% of the relationships finished early
  20% finished on-time
  61% of them finished late
When just critical relationships considered
  20% of the relationships finished early
  22% finished on-time
  58% of them finished late

## Slide 28: Benchmarking Relationships
In general,
  20% of the relationships finished early
  20% finished on-time
  60% of them finished late
Other statistics,
  87% schedules used lags greater than zero
  24% schedules used negative lags
  Average longest lag was 86 days

## Slide 29: Non-Zero Lag Accuracy
Planned non-zero lags require intention
  How accurate were the estimates?
Planned negative lags
  Average finished 4 days later than planned
  Standard deviation of 18 days
Planned positive lags
  Average finished 17 days later than planned
  Standard deviation of 18 days

## Slide 30: Scheduler’s Short-Cut
Plan FS/0 with intention of starting early
  Simplifies As-Planned Schedule
  Overcomes owner objections
Actual start less than 3 days early (1-2 days)
  98% of schedules showed some instances
  1 out of 46 did not have scheduler’s short-cut
  2 schedules had 30% short-cuts
  Average was 8% of all relationships

## Slide 31
2025 Construction CPM Conference The Future of Relationship Tracking

## Slide 32: RDCPM™ Certification
Report on merge bias ‘mini-milestones’
User-definable relationship codes
Text narratives for relationships
Select relationships by predecessor and/or successor codes
Expand the types of relationships
Treat lags like activity durations
  Allow calendars and duration types to be assigned
Relationship Diagramming Method

## Slide 33: RDCPM™ Certification
Automatic lag modifications based on productivity
Complex logic based on rule sets
Improved handling of out-of-sequence progress
  Change FS to FF
Expand float measurement types
  Multi-calendar float
  Path free float

## Slide 34: Future of Rel Tracking
Some vendors have earned partial RDCPM™ certification
Also needed
  Add the display of remaining lag duration
  Add the display of actual lag duration
  Add lag As-Planned/As-Built variance
  Sort relationship reports based on planned lag

## Slide 35
2025 Construction CPM Conference Conclusions

## Slide 36: Conclusions
Switch from ADM to PDM software
  Overlooked reporting on relationships
Relationships have many unused properties
  Only limited by software offerings
Consumption of relationship float
  Analysis can lead to better project management

## Slide 37: Conclusions
Benchmark relationship performance
  Can be limited to just critical relationships
General benchmarking averages
  20% finish early
  20% finish on-time
  60% finish late
  Holds true with general population and critical

## Slide 38: Conclusions
Benchmark in-general findings
  Planned negative lags are better estimated
  Planned positive lags planned better than 0 lags
Scheduler’s Shortcut is a real phenomenon
  Approximately 8% of all FS/0 relationships
  High of around 30%

## Slide 39: Conclusions
Future of CPM
  Enhanced reporting of relationship statistics
  Remaining lag and actual lag needed now
  Up to software companies to meet the need

## Slide 40
2025 Construction CPM Conference
Questions?
Ron Winter, PSP, FAACE
Schedule Analyzer Software
ron@ronwinterconsulting.com