## Slide 1
2025 Construction CPM Conference Mastering Out-of-Sequence Progress
Ron Winter, PSP, FAACE
Schedule Analyzer Software

## Slide 2: Ron Winter, PSP, FAACE
Bachelor of Science in Engineering
Construction Scheduler
US Air Force Navigator
Construction Scheduler
Master of Science in Systems Management
Programmer, Project Manager, Customer Support, and Industrial Trainer
Construction Scheduler
Developer of Schedule Analyzer Software

## Slide 3: Definition
Out-of-Sequence Progress
  When an activity actually begins before the existing logic and predecessor activity’s status allows
  When actual dates occur prior to logically computed dates (actual start or actual finish)
  Abbreviated here as, “OOS”

## Slide 4: Introduction
Why is out-of-sequence important?
Review of major concepts (properties)
Present out-of-sequence benchmarks
Out-of-Sequence reporting options
  Text reports
  Graphical analysis technique
Out-of-sequence report for MS Project
  Better than the one P6 currently has

## Slide 5
2025 Construction CPM Conference Out-of-Sequence Importance

## Slide 6: Why is OOS Important?
Was the project plan reasonable?
  Is it logic driven?
Is the schedule being followed?
  Time for a recovery plan?
  Schedule may be show on-time
Can the schedule be used for analysis?
  Does it properly predict project completion?
  Can it be used for a TIA?

## Slide 7: Account for Disruptions
OOS are ‘minor’ disruptions to a project
  May appear to initially be insignificant
They are documented in schedule
  Accumulated changes over time may be significant
Create Half-Step Schedule for all updates
  Will display all out-of-sequence work
How severe is it out-of-sequence?
  We need to understand OOS properties

## Slide 8
2025 Construction CPM Conference Out-of-Sequence Properties

## Slide 9: Direct vrs. Indirect OOS
Directly Out-of-Sequence
  An activity that logically starts prior to immediate predecessor activity
Indirectly Out-of-Sequence
  An activity that starts prior some logically distant activity
  It may even logically start after immediate predecessor activity

## Slide 10
Necking ‘proves’ out-of-sequence
Direct vrs. Indirect OOS

## Slide 11: Identifying Indirect
Follow successors from direct OOS act

## Slide 12: Active vers. Inactive
Active Out-of-Sequence activities
  Retained Logic delays re-start
  Causes a ‘gap’ in barchart figures
Inactive Out-of-Sequence activities
  Still out-of-sequence
  Retained Logic no longer delays re-start
  Due to predecessor activity being complete
  Some CPM software do not report this

## Slide 13: Active vers. Inactive

## Slide 14: Types of OOS
Predecessor Complete | Predecessor Incomplete
Inactive / Direct | Active / Direct
Inactive / Indirect | Active / Indirect

## Slide 15: OOS and Software
Reports Inactive & Active / Direct & Indirect
  SA Forensic
Reports Inactive & Active Direct
  Netpoint / Schedule Analyzer / Spider / Syncro / Open Plan / Power Project
Reports only Active Direct
  P6 Professional
    We can make P6 report Active Direct & Indirect
    New P6 report filter

## Slide 16: P6 Filter for All Active
Set a activity filter for
  Activity has an Actual Start
  Early Start date > Data Date
  Both must be present

## Slide 17: Events/OOS Activities
Every relationship executed out-of-sequence is an event
An out-of-sequence activity can have more than one out-of-sequence predecessor
  More than one event
An activity with multiple events is more severely out-of-sequence than just one

## Slide 18: Events vrs. Activities
OOS Act 1 started early to one activity
OOS Act 2 started early on three activities

## Slide 19: Degree of Early Start
The number of days started early matters
  Maybe starting slightly early does not matter
Common construction practice to begin follow-on work a day or two early
  Calling this FS/0 is a “scheduler’s short cut”
Starting weeks/months early is more severe
Finishing the out-of-sequence activity is more severe as well

## Slide 20: Properties Summary
Direct versus Indirect OOS
Current versus historic out-of-sequence
  Active versus Inactive OOS
Tracking OOS logic events vers. activities
Degree (duration) of the early start

## Slide 21
2025 Construction CPM Conference Benchmarking Out-of-Sequence

## Slide 22: Statistical Findings
Analyzed 46 independent construction schedules
All four types identified
 | Started Acts | Ave Early (WD) | Direct Events | Direct Acts | Indirect Events | Indirect Acts | Total Events | OOS Acts | % Acts OOS | Events /OOS
Average | 1661 | 54 | 1089 | 489 | 266 | 79 | 1342 | 568 | 40% | 1.65
Median | 734 | 47 | 296 | 227 | 104 | 32 | 360 | 250 | 38% | 1.52
St. Dev. | 2476 | 39 | 2188 | 805 | 506 | 182 | 2502 | 875 | 18% | 1.01

## Slide 23: Early Starts
OOS early starts greater than one standard deviation:
  Mean (average): 45 work days
  Standard Deviation: 48
  Failure (more than one standard deviation)
    Average overlap greater than 45 + 48 = 93 work days

## Slide 24: Percent of OOS
Percent of OOS activities greater than one standard deviation:
  Mean: 40%
  Standard Deviation: 18%
  Failure (more than one standard deviation)
    Average percentage greater than 40 + 18 = 58%

## Slide 25: Benchmark Results
Of the 46 schedules evaluated
  Ten exceeded mean of early starts
  Six exceeded the mean percentage of OOS
  One schedule exceeded both benchmarks

## Slide 26
2025 Construction CPM Conference Industry Out-of-Sequence Reports

## Slide 27: Types of Reports
When report lists OOS relationships
  Allows for event statistics
    Netpoint / Schedule Analyzer / Spider / Syncro
When the OOS report only lists the activity
  Cannot count events
    Open Plan / P6 / Power Project

## Slide 28: What Could be Reported
Out-of-sequence & predecessor activities
Total float
Applicable Dates
Relationship type and lag
Work and calendar days early start
Reason activity was out-of-sequence
OOS Pred Float Date Description
——————————————— ——————————————— ————— ———————————————— ————————————————————————————————————
575.CMOB.LA.100 519 S=01AUG13-00:00A LA - CONSTRUCTION MOBILIZATION - 33%
575.PM.120 0 F=28AUG13-08:00A FULL NOTICE TO PROCEED
——————————————— ——————————————— ————— ———————————————— ————————————————————————————————————
Rel/Lag=FS/0, WorkDays-Early=27.00, CalendarDays-Early=27.00
Problem: Activity started, predecessor has not finished.

## Slide 29: Possible Statistics
————————————————————————————
RELATIONSHIP OUT-OF-SEQUENCE
SCHEDULE QUALITY STATISTICS
————————————————————————————
Total Number of Started Activities with Predecessors: 12295
Direct Out-of-Sequence Activities : 3021
Indirect Out-of-Sequence Activities : 239
Total Number of Out-of-Sequence Activities : 3260
Both Direct and Indirect Activity (not counted) : 547
Percentage of Out-of-Sequence Acts : 26.51%
Total Direct Out-of-Sequence Events : 4271
Total Indirect Out-of-Sequence Events : 1130
Number of Active Direct OOS Activities : 623
Number of Active Indirect OOS Activities : 239
Total Number of Active OOS Activities : 862
Average Length of Early Starts: 82.21 days
Summary of Direct Out-of-Sequence Totals for Reason Types:
3209 Activities started, predecessor has not finished.
7 Activities started before its predecessor's lag would allow.
136 Activities started, predecessor has not started.
310 Activities finished, predecessor not started.
573 Activities started too early to allow it to finish on time.
36 Activities with lag started too early to allow it to finish on time.
Additional Reasons:
2003 Activities finished, predecessor has not finished.
19 Activities finished before its predecessor's lag would allow.

## Slide 30: Graphical Analysis
Daily work profile
Percent of out-of-sequence
Events versus Activities
Profile without holidays
Target only early starts
Early start histogram

## Slide 31: Calculate Work Profile
Plot the start/finish of each OOS activity
Add up each daily total

## Slide 32: Typical Graph
How closely did OOS parallel total work?

## Slide 33: Track % of OOS
Once work really started it held steady at 20%
Start of major work

## Slide 34: Events vers. Activities
Chart: 
Total OOS Events
OOS Activities
Daily totals of OOS activities

## Slide 35: Profile No Holidays
Chart: 
Best Used Over Short Periods

## Slide 36: Target Early Starts
Ignore part of OOS not out-of-sequence
  Identify the portion that is truly OOS

## Slide 37: Example Early Starts
Chart: 
OOS After
OOS Before
Events After
Events Before

## Slide 38: Early Start Histogram

## Slide 39
2025 Construction CPM Conference Program Project for Out-of-Sequence

## Slide 40: Project OOS Reporting
Not a ‘built-in’ Microsoft Project feature
Report added using Visual Basic (VBA)
Can be permanently used on all schedules
Given here as free open-source program
Works on all versions of MS Project

## Slide 41: Creating OOS Report
Tabs
Ribbon Bar
Add the Developer Tab
Right-Click Ribbon Bar

## Slide 42: Creating OOS Report
Click on Customize the Ribbon

## Slide 43: Creating OOS Report
Click on Developer checkbox
Click on OK button

## Slide 44: Creating OOS Report
Click on Developer tab
Click on Visual Basic button

## Slide 45: Creating OOS Report
Expand ProjectGlobal
Expand Project Objects
Double-click on ThisProject
Maximize Programming Window Area

## Slide 46: Creating OOS Report
Copy VB code
  Paper
  File
Right-click program window
Paste

## Slide 47: Download VBA Program
ScheduleAnalyzer.com/eforensic_OOS_Survey.htm

## Slide 48: Creating OOS Report
End of program shown here

## Slide 49: Creating OOS Report
Save program
  File/Save
Close
  File/Close
Returns to MS Project

## Slide 50: Creating OOS Report
Set-up display
Right-click column header
Click on Insert Column

## Slide 51: Creating OOS Report
Click on Unique ID
  Internally assigned
  Never changes

## Slide 52: Creating OOS Report
Repeat
Right-click column header
Click on Insert Column

## Slide 53: Creating OOS Report
Click on Text30
  Last User- defined field
  Use this for report output

## Slide 54
2025 Construction CPM Conference Out-of-Sequence Report for Project

## Slide 55: Running OOS Report
Run Out-of- Sequence Report
Click on Developer tab

## Slide 56: Running OOS Report
Click on View Macros button
  Macros
  Code
  Scripts
Can add button

## Slide 57: Running OOS Report
Select CheckOutOfSequence
Click on Run button

## Slide 58: Running OOS Report
Last chance to ‘chicken-out’
  Use in case the macro accidently was selected

## Slide 59: Running OOS Report
Report Calculations are complete
Statistics displayed
  # Tasks started
  # OOS acts
  # OOS events
  % tasks OOS
  Average early start
Click OK button

## Slide 60: MS Project OOS Report
Text30
  Unique ID
  Predecessor Unique IDs
Shown left
  UID #20 OOS
  To UID #18
  Blank = not OOS

## Slide 61
2025 Construction CPM Conference Recap

## Slide 62: Types of OOS
Direct Out-of-Sequence
  Activity started before immediate predecessor finished
Indirect Out-of-Sequence
  Activity started earlier than distant predecessor
Direct Out-of-Sequence
Indirect Out-of-Sequence

## Slide 63: Types of OOS
Inactive Out-of-Sequence
  Predecessor is complete
Active Out-of-Sequence
  Predecessor has not completed as of the data date
  This is what our New Technique reports
Inactive | Active

## Slide 64: Types of OOS
Put this together
Most CPM software only report
  Inactive Direct OOS
  Active Direct OOS
Inactive Direct Out-of-Sequence | Active Direct Out-of-Sequence
Inactive Indirect Out-of-Sequence | Active Indirect Out-of-Sequence

## Slide 65: Types of OOS
P6 Professional reports on this
  Direct OOS, predecessor is incomplete
New P6 filter reports on this
  Activity started
  Early Start greater than Data Date
Inactive Direct Out-of-Sequence | Active Direct Out-of-Sequence
Inactive Indirect Out-of-Sequence | Active Indirect Out-of-Sequence

## Slide 66: Types of OOS
No software reported on this
  Indirect OOS and the predecessor is complete
Except Schedule Analyzer Forensic
Inactive Direct Out-of-Sequence | Active Direct Out-of-Sequence
Inactive Indirect Out-of-Sequence | Active Indirect Out-of-Sequence

## Slide 67
2025 Construction CPM Conference
Questions?
Ron Winter, PSP, FAACE
Schedule Analyzer Software
ron@ronwinterconsulting.com